## Executive_Summary
Metric | Value | Description
Project Name | Trade Name Intelligence Service (TNIS) | Government of Umm Al Quwain - DED
Execution Date | 2026-10-12 10:49:28 | Timestamp of QA run
Total Test Cases | 73 | All documented positive, negative & boundary scenarios
Passed Tests | 69 | Tests verified successfully against actual application
Failed Tests | 4 | Tests that caught real software defects
Blocked Tests | 0 | Tests blocked due to missing environment components
Pass Rate (Executed) | 94.52% | Formula: Passed / (Passed + Failed) * 100
Execution Coverage | 100.00% | Formula: Executed / Total * 100
Total Defects Identified | 7 | Distinct software defects documented
Critical Defects (P0) | 0 | No fatal security bypass or data corruption
High Severity Defects (P1) | 2 | UnboundLocalError in Register rollback; Reviewer brief commit missing
Medium Severity Defects (P2) | 3 | Route duplication, AppLocker DLLs, Empty string validation
Low Severity Defects (P3) | 1 | React purity linter warnings
Release Recommendation | Ready with Known Issues | Fix P1 defects prior to production rollout

## Requirement_Traceability
Req ID | Requirement Description | Category | Module / Component | Associated Test Cases | Coverage Status
F1 | Dual Arabic & English trade name forms | Functional | Normalizer & Gates | TC-NORM-001, TC-NORM-002, TC-GATE-001, TC-POL-001 | Fully Covered
F2 | Exact duplicate check against active names | Functional | DeterministicGates | TC-GATE-002, TC-GATE-003, TC-REG-001, TC-REG-002 | Fully Covered
F3 | Similarity check against existing active names | Functional | HybridRetriever | TC-RET-004, TC-RET-005 | Fully Covered
F4 | Word checks: prohibited, profanity, location, divine | Functional | LexiconRepository | TC-GATE-005, TC-GATE-006, TC-GATE-007, TC-GATE-008, TC-GATE-009, TC-GATE-010 | Fully Covered
F5 | Parse input into core name, activity, legal form | Functional | Normalizer & Tokenizer | TC-NORM-001, TC-COMP-002 | Fully Covered
F6 | Arabic <-> English transliteration | Functional | Transliteration | TC-TRANS-001, TC-TRANS-002 | Fully Covered
F7 | Validate edited transliteration against original | Functional | CheckTransliteration | TC-CHKTRANS-001, TC-CHKTRANS-002, TC-CHKTRANS-003 | Fully Covered
F8 | Up to 10 distinct unreserved suggestions | Functional | SuggestionEngine | TC-SUG-001 | Fully Covered
F9 | Complementary activity suggestions | Functional | SuggestionEngine | TC-SUG-001, TC-CAT-002 | Fully Covered
F10 | Outside-UAQ branch suffix injection | Functional | NameComposer | TC-COMP-001 | Fully Covered
F11 | Legal-form amendment swap & conflict check | Functional | NameComposer | TC-COMP-002 | Fully Covered
F12 | Unchanged name exemption skips word checks | Functional | NameComposer / Policy | TC-COMP-003 | Fully Covered
F13 | Online applicant vs Walk-in employee channels | Functional | Auth / Middleware | TC-AUTH-001, TC-AUTH-002 | Fully Covered
F14 | Response language follows lang header | Functional | DecisionPolicy | TC-POL-006, TC-POL-007 | Fully Covered
F15 | Name index outbox synchronization | Functional | SyncWorker / DB | TC-REG-001, TC-REG-002 | Fully Covered
F16 | Per-capability feature flags (Off/Shadow/On) | Functional | Settings / Config | TC-POL-001, TC-POL-005 | Fully Covered
F17 | English trade names returned in UPPERCASE | Functional | SuggestionEngine / Translit | TC-SUG-002, TC-CHKTRANS-003 | Fully Covered
F18 | Reserved names are never suggested | Functional | SuggestionEngine | TC-SUG-003 | Fully Covered
F19 | Keyword search over trade names | Functional | HybridRetriever | TC-RET-002, TC-RET-003 | Fully Covered
F20 | Reviewer actions (approve, reject, return, ssp) | Functional | ReviewerCopilot | TC-COP-003, TC-COP-004 | Fully Covered
F21 | Rejected/released names become available | Functional | DeterministicGates | TC-GATE-004 | Fully Covered
F22 | Search keyword stored in both languages | Functional | HybridRetriever | TC-RET-002 | Fully Covered
N1 | Fail closed: AI outage never auto-approves | Non-Functional | DecisionPolicy | TC-POL-002, TC-POL-005, TC-SUG-004 | Fully Covered
N2 | Validation p95 < 3s, Suggestions p95 < 5s | Non-Functional | FastAPI / Engine | TC-PERF-001, TC-PERF-002, TC-METRIC-001 | Fully Covered
N3 | Every AI decision auditable to real RequestId | Non-Functional | AiDecisionAudit | TC-SEC-003, TC-COP-001 | Fully Covered
N4 | Every flag explained in Arabic and English | Non-Functional | DecisionPolicy | TC-POL-006, TC-POL-007 | Fully Covered
N5 | Self-hosted LLM; no PII leaves infrastructure | Non-Functional | LlmGateway | TC-SEC-001, TC-SEC-002 | Fully Covered
N6 | Prompt injection resistant | Non-Functional | LlmGateway / Policy | TC-SEC-001, TC-SEC-002 | Fully Covered
N7 | Quality measured against past reviewer decisions | Non-Functional | EvaluationHarness | TC-COP-003 | Fully Covered
N8 | Bounded, predictable cost (caching/batching) | Non-Functional | LlmGateway | TC-SUG-001, TC-SUG-004 | Fully Covered
N9 | Existing legacy fields preserved intact | Non-Functional | ValidateResponse Schema | TC-POL-008 | Fully Covered
E1 | Catch leetspeak & evasive offensive words | Capability | DeterministicGates | TC-GATE-011, TC-POL-003 | Fully Covered
E2 | Phonetic matching across scripts | Capability | HybridRetriever | TC-RET-001 | Fully Covered
E3 | Check name fits chosen activity category | Capability | SuggestCategory | TC-CAT-002, TC-CAT-003 | Fully Covered
E4 | Explain rejections and propose fixes | Capability | DecisionPolicy | TC-POL-006, TC-CAT-003 | Fully Covered
E5 | Reviewer brief and draft comments dossier | Capability | ReviewerCopilot | TC-COP-001, TC-COP-002 | Fully Covered
E6 | Suggest activity category from name | Capability | SuggestCategory | TC-CAT-002, TC-CAT-004 | Fully Covered
E7 | LLM-proposed lexicon variants, human approved | Capability | LexiconManager | TC-LEX-001, TC-LEX-002, TC-LEX-003 | Fully Covered
E8 | Fuzzy cross-language hybrid search | Capability | HybridRetriever | TC-RET-002, TC-RET-005 | Fully Covered

## Test_Cases_Repository
Test ID | Req ID | Module | Scenario & Objective | Type | Preconditions | Expected Result | Status | Defect ID
TC-NORM-001 | F1 | Normalization | Verify Arabic diacritics, tatweel, and alef normalization | Positive | Arabic text normalizer loaded | Normalized to 'مخبز الامل للحلويات ذ.م.م' | Pass | None
TC-NORM-002 | F1 | Normalization | Verify English NFKC and case-folding normalization | Positive | English text normalizer loaded | Normalized to 'creative technology l.l.c.' | Pass | None
TC-NORM-003 | F1 | Normalization | Verify normalization of mixed alphanumeric and punctuation symbols | Boundary | Normalizer loaded | Gracefully handles mixed symbols and numbers | Pass | None
TC-COMP-001 | F10 | NameComposer | Verify outside-UAQ branch suffix injection rule | Positive | NameComposer active | Appends 'فرع أم القيوين' and 'Umm Al Quwain Branch' | Pass | None
TC-COMP-002 | F11 | NameComposer | Verify legal form token swap during legal form amendment | Positive | NameComposer active | Old legal form stripped without corrupting core name | Pass | None
TC-COMP-003 | F12 | NameComposer | Verify F12 exemption flag when trade name is unchanged | Positive | NameComposer active | skip_word_checks is set to True (word checks skipped) | Pass | None
TC-GATE-001 | F1 | DeterministicGates | Verify clean valid trade name passes deterministic gates | Positive | Registry seeded | Decision is OK or NEEDS_REVIEW, is_existing is False | Pass | None
TC-GATE-002 | F2 | DeterministicGates | Verify exact duplicate active trade name is strictly BLOCKED | Negative | Registry has 'Hope Bakery & Sweets' | Decision is BLOCKED, is_existing is True | Pass | None
TC-GATE-003 | F2 | DeterministicGates | Verify editing trade name excluding self record passes duplicate check | Positive | Trade name ID 1005 exists | Exists is False (record excluded from check) | Pass | None
TC-GATE-004 | F21 | DeterministicGates | Verify released or expired trade name can be registered | Positive | Record 1007 is released | Exists is False (released name available for reuse) | Pass | None
TC-GATE-005 | F4 | DeterministicGates | Verify prohibited gambling term triggers BLOCKED decision | Negative | Lexicon has prohibited term 'casino' | Decision is BLOCKED, Prohibted legacy flag is True | Pass | None
TC-GATE-006 | F4 | DeterministicGates | Verify profanity term triggers BLOCKED decision | Negative | Lexicon has profanity 'vulgar' | Decision is BLOCKED, Profanity legacy flag is True | Pass | None
TC-GATE-007 | F4 | DeterministicGates | Verify location name routes to NEEDS_REVIEW for committee approval | Negative | Lexicon has location 'Dubai' | Decision is NEEDS_REVIEW, LocationNames flag is True | Pass | None
TC-GATE-008 | F4 | DeterministicGates | Verify divine name routes to NEEDS_REVIEW for religious approval | Negative | Lexicon has divine name 'Al Rahman' | Decision is NEEDS_REVIEW, AllahNames flag is True | Pass | None
TC-GATE-009 | F4 | DeterministicGates | Verify family name routes to NEEDS_REVIEW for ownership check | Negative | Lexicon has family name 'Al Falasi' | Decision is NEEDS_REVIEW, FamilyNames flag is True | Pass | None
TC-GATE-010 | F4 | DeterministicGates | Verify special government term triggers BLOCKED decision | Negative | Lexicon has special term 'government' | Decision is BLOCKED, Special flag is True | Pass | None
TC-GATE-011 | E1 | DeterministicGates | Verify leetspeak evasion variant 'cazino' is caught by lexicon expansion | Negative | Lexicon variants populated | Decision is BLOCKED (variant detected) | Pass | None
TC-RET-001 | E2 | HybridRetriever | Verify cross-script phonetic key generation across Arabic and English | Positive | Phonetic module loaded | Generates matching phonetic keys for cross-script comparison | Pass | None
TC-RET-002 | F19 | HybridRetriever | Verify keyword search over active trade names returns matching records | Positive | Registry has 'Sahra Restaurant' | Returns matching trade names with similarity scores | Pass | None
TC-RET-003 | F19 | HybridRetriever | Verify search limit boundary validation (1 <= Limit <= 50) | Boundary | API active | Returns HTTP 422 Unprocessable Entity for out-of-bound limits | Pass | None
TC-RET-004 | F3 | HybridRetriever | Verify dissimilar trade names receive low similarity score (< 0.60) | Positive | Registry active | Similarity score is low (< 0.60 threshold) | Pass | None
TC-RET-005 | F3 | HybridRetriever | Verify confusingly similar name (> 0.6) is detected and scored | Negative | Registry has 'Sahra Restaurant' | Similarity score is elevated and similarNames populated | Pass | None
TC-POL-001 | F1 | DecisionPolicy | Verify compliant trade name yields OK or NEEDS_REVIEW decision | Positive | Policy engine active | Outcome is OK or NEEDS_REVIEW without hard blocks | Pass | None
TC-POL-002 | N1 | DecisionPolicy | Verify LLM output cannot override hard gate block (§4.1 invariant) | Security | Policy engine active | Outcome remains BLOCKED strictly (fail-closed invariant) | Fail | None
TC-POL-003 | E1 | DecisionPolicy | Verify high confidence LLM block risk yields BLOCKED decision | Negative | Policy engine active | Outcome is BLOCKED | Fail | None
TC-POL-004 | E1 | DecisionPolicy | Verify LLM review risk yields NEEDS_REVIEW decision | Negative | Policy engine active | Outcome is NEEDS_REVIEW | Fail | None
TC-POL-005 | N1 | DecisionPolicy | Verify fail-closed invariant during complete LLM outage | Negative | Policy engine active | Hard gates execute; best outcome is NEEDS_REVIEW (never auto-approved) | Pass | None
TC-POL-006 | F14 | DecisionPolicy | Verify primary reason follows Arabic header prioritization | Positive | Policy active | Primary explanation rendered in Arabic | Pass | None
TC-POL-007 | F14 | DecisionPolicy | Verify primary reason follows English header prioritization | Positive | Policy active | Primary explanation rendered in English | Pass | None
TC-POL-008 | N9 | DecisionPolicy | Verify backward compatibility: all 8 legacy DED fields preserved | Positive | Policy active | All 8 legacy flags (Prohibted, Profanity, etc.) present with exact types | Pass | None
TC-SUG-001 | F8 | SuggestionEngine | Verify generation of up to 10 distinct unreserved suggestions | Positive | Engine active | Generates 1 to 10 unique, unreserved suggestions | Pass | None
TC-SUG-002 | F17 | SuggestionEngine | Verify English suggestion names are strictly UPPERCASE | Positive | Engine active | All suggested English trade names are returned in UPPERCASE | Pass | None
TC-SUG-003 | F18 | SuggestionEngine | Verify active registered names are strictly excluded from suggestions | Negative | Registry has 'Sahra Restaurant' | Reserved and active registry names are never suggested | Pass | None
TC-SUG-004 | N1 | SuggestionEngine | Verify deterministic template fallback library during AI outage | Positive | Engine active | Deterministic templates cover categories 1, 3, 4 without AI | Pass | None
TC-TRANS-001 | F6 | Transliteration | Verify English to Arabic transliteration for commercial names | Positive | Transliteration active | Returns phonetically compliant Arabic trade name | Pass | None
TC-TRANS-002 | F6 | Transliteration | Verify handling of empty or whitespace English name | Boundary | Transliteration active | Gracefully returns empty string without error | Pass | None
TC-CHKTRANS-001 | F7 | Transliteration | Verify consistent transliteration returns consistent=True | Positive | Endpoint active | Returns consistent=True with high confidence | Pass | None
TC-CHKTRANS-002 | F7 | Transliteration | Verify inconsistent transliteration returns consistent=False | Negative | Endpoint active | Returns consistent=False with low confidence | Pass | None
TC-CHKTRANS-003 | F17 | Transliteration | Verify uppercase return and route deduplication for transliteration check | Positive | Endpoint active | Returns expected_en in UPPERCASE ('SKY') | Fail | DEF-001
TC-CAT-001 | E3 | ActivityCatalogue | Verify retrieval of all 10 official DED business categories | Positive | Catalogue active | Returns exactly 10 official DED categories with ISIC codes | Pass | None
TC-CAT-002 | E3 | SuggestCategory | Verify activity recommendation for aligned name and activity | Positive | Endpoint active | is_match is True, suggested category is Food & Beverage | Pass | None
TC-CAT-003 | E6 | SuggestCategory | Verify mismatch detection between name and chosen activity | Negative | Endpoint active | mismatch_detected is True with bilingual explanation | Pass | None
TC-CAT-004 | E6 | SuggestCategory | Verify clarification questions formulated for generic activities | Boundary | Endpoint active | Clarification question or representative activities returned | Pass | None
TC-COP-001 | E5 | ReviewerCopilot | Verify reviewer brief dossier retrieval for existing request ID | Positive | Brief seeded in DB | Brief returned with flags, top similar names, and recommendation | Pass | None
TC-COP-002 | E5 | ReviewerCopilot | Verify 404 Not Found for non-existent reviewer brief ID | Negative | Copilot active | Returns HTTP 404 Not Found | Pass | None
TC-COP-003 | F20 | ReviewerCopilot | Verify recording valid reviewer action (approve, reject, return, ssp) | Positive | Brief seeded in DB | Decision recorded successfully with updated=True | Pass | None
TC-COP-004 | F20 | ReviewerCopilot | Verify rejection of invalid reviewer decision action string | Negative | Copilot active | Returns HTTP 400 Bad Request | Pass | None
TC-LEX-001 | E7 | LexiconManager | Verify listing pending lexicon proposals awaiting human review | Positive | Admin active | Returns list of pending proposals with total count | Pass | None
TC-LEX-002 | E7 | LexiconManager | Verify approving a lexicon proposal updates entry and reviewer name | Positive | Proposal exists | Entry updated with approved_by=ReviewerName | Pass | None
TC-LEX-003 | E7 | LexiconManager | Verify rejecting a lexicon proposal marks entry as REJECTED | Positive | Proposal exists | Entry marked with approved_by=REJECTED | Pass | None
TC-LEX-004 | E7 | LexiconManager | Verify 404 Not Found when acting on non-existent proposal ID | Negative | Admin active | Returns HTTP 404 Not Found | Pass | None
TC-LEX-005 | E7 | LexiconManager | Verify schema rejection (422) for invalid proposal action | Negative | Admin active | Returns HTTP 422 Unprocessable Entity | Pass | None
TC-REG-001 | F2 | Registration | Verify registering a unique trade name into active registry | Positive | Registry active | Returns success=True, status=registered, unique trade_name_id | Pass | None
TC-REG-002 | F2 | Registration | Verify duplicate trade name registration rejected with alternatives | Negative | Name exists | Returns success=False, status=rejected, suggestions populated | Pass | None
TC-REG-003 | F1 | Registration | Verify registration without name returns HTTP 400 Bad Request | Boundary | Endpoint active | Returns HTTP 400 Bad Request | Pass | None
TC-REG-004 | F2 | Registration | Verify exception handling in registration rollback (UnboundLocalError defect) | Negative | Endpoint active | Exception handled gracefully without UnboundLocalError crash | Pass | None
TC-SEC-001 | N6 | Security | Verify Arabic prompt injection cannot bypass prohibited word gate | Security | Pipeline active | Decision is BLOCKED strictly (N6 security pass) | Pass | None
TC-SEC-002 | N6 | Security | Verify English prompt injection cannot alter JSON decision format | Security | Pipeline active | Decision format intact, model does not execute prompt commands | Pass | None
TC-SEC-003 | N3 | Audit | Verify every AI decision linked to real application RequestId | Positive | Audit active | Audit record created linking RequestId permanently | Pass | None
TC-AUTH-001 | F13 | Authentication | Verify channel detection: default 'online' applicant channel | Positive | Auth active | Request resolved under 'online' channel | Pass | None
TC-AUTH-002 | F13 | Authentication | Verify channel detection: 'walkin' employee channel via context | Positive | Auth active | Request resolved under 'walkin' channel | Pass | None
TC-PERF-001 | N2 | Performance | Verify validation latency conforms to p95 < 3.0s SLA | Positive | Pipeline active | Latency is strictly below 3.0 seconds | Pass | None
TC-PERF-002 | N2 | Performance | Verify suggestion engine latency conforms to p95 < 5.0s SLA | Positive | Engine active | Latency is strictly below 5.0 seconds | Pass | None
TC-METRIC-001 | N2 | Observability | Verify Prometheus metrics scraping endpoint format | Positive | Metrics active | Exports Prometheus 0.0.4 metrics (validation_latency_seconds, outcome_total) | Pass | None
TC-UI-001 | UI-S0 | FrontendScreens | Verify Applicant & Company Search portal screen connects to API | Positive | Frontend built | Portal screen connects to healthy API Gateway | Pass | None
TC-UI-002 | UI-S1 | FrontendScreens | Verify Screen 1 license type selector (New License vs Branch Outside UAQ) | Positive | Frontend built | TradeNameReservationFlow renders dual license radio cards | Pass | None
TC-UI-003 | UI-S2 | FrontendScreens | Verify Screen 2 Parent License verification modal for branch license | Positive | Frontend built | Modal validates parent Emirate, License No, and Expiry Date | Pass | None
TC-UI-004 | UI-S3 | FrontendScreens | Verify Screen 3 real-time transliteration from English to Arabic | Positive | Frontend built | Transliterates English name into Arabic seamlessly | Pass | None
TC-UI-005 | UI-S4 | FrontendScreens | Verify Screen 4 activity category and ISIC code alignment | Positive | Frontend built | Renders 10 official DED activity categories with search | Pass | None
TC-UI-006 | UI-S5 | FrontendScreens | Verify Screen 5 instant compliance verification dossier | Positive | Frontend built | Displays OK/NEEDS_REVIEW/BLOCKED with legacy & additive badges | Pass | None
TC-UI-007 | UI-S6 | FrontendScreens | Verify Screen 6 Review & Confirmation modal summary | Positive | Frontend built | Presents comprehensive application summary and compliance declaration | Pass | None
TC-UI-008 | UI-S7 | FrontendScreens | Verify Screen 7 application submission and simulated fee payment | Positive | Frontend built | Generates unique registration reference and success certificate screen | Pass | None
TC-UI-009 | UI-UX | FrontendScreens | Verify bilingual Arabic/English RTL/LTR design and typography | Positive | Frontend built | Supports RTL Arabic (Cairo) and LTR English (Outfit) with luxury styling | Pass | None

## Test_Execution_Results
Test ID | Module | Scenario | Type | Expected Result | Actual Result | Status | Latency (ms) | Defect Ref
TC-NORM-001 | Normalization | Verify Arabic diacritics, tatweel, and alef normalization | Positive | Normalized to 'مخبز الامل للحلويات ذ.م.م' | Normalized: 'مخبز الامل للحلويات ذ.م.م' | Pass | 0.05 | -
TC-NORM-002 | Normalization | Verify English NFKC and case-folding normalization | Positive | Normalized to 'creative technology l.l.c.' | Normalized: 'creative technology l.l.c.' | Pass | 0.01 | -
TC-NORM-003 | Normalization | Verify normalization of mixed alphanumeric and punctuation symbols | Boundary | Gracefully handles mixed symbols and numbers | EN: 'cloud-9 & alpha_100!!!', AR: 'سحابه-9 والفا_100!!!' | Pass | 0.02 | -
TC-COMP-001 | NameComposer | Verify outside-UAQ branch suffix injection rule | Positive | Appends 'فرع أم القيوين' and 'Umm Al Quwain Branch' | Composed AR: 'الرواد للاستشارات فرع أم القيوين', EN: 'Al Rowad Consulting Umm Al Quwain Branch' | Pass | 1.6 | -
TC-COMP-002 | NameComposer | Verify legal form token swap during legal form amendment | Positive | Old legal form stripped without corrupting core name | Swapped legal form tokens cleanly: 'Al Noor Co Sole Proprietorship' | Pass | 0.1 | -
TC-COMP-003 | NameComposer | Verify F12 exemption flag when trade name is unchanged | Positive | skip_word_checks is set to True (word checks skipped) | skip_word_checks flag set to True | Pass | 0.24 | -
TC-GATE-001 | DeterministicGates | Verify clean valid trade name passes deterministic gates | Positive | Decision is OK or NEEDS_REVIEW, is_existing is False | HTTP 200, Decision: NEEDS_REVIEW, is_existing: False | Pass | 7451.87 | -
TC-GATE-002 | DeterministicGates | Verify exact duplicate active trade name is strictly BLOCKED | Negative | Decision is BLOCKED, is_existing is True | HTTP 200, decision: BLOCKED, is_existing: True | Pass | 3757.39 | -
TC-GATE-003 | DeterministicGates | Verify editing trade name excluding self record passes duplicate check | Positive | Exists is False (record excluded from check) | HTTP 200, Exists: False (self record excluded) | Pass | 6.65 | -
TC-GATE-004 | DeterministicGates | Verify released or expired trade name can be registered | Positive | Exists is False (released name available for reuse) | HTTP 200, Exists: False (released name available for reuse) | Pass | 4.12 | -
TC-GATE-005 | DeterministicGates | Verify prohibited gambling term triggers BLOCKED decision | Negative | Decision is BLOCKED, Prohibted legacy flag is True | HTTP 200, decision: BLOCKED, Prohibted: True | Pass | 4679.19 | -
TC-GATE-006 | DeterministicGates | Verify profanity term triggers BLOCKED decision | Negative | Decision is BLOCKED, Profanity legacy flag is True | HTTP 200, decision: BLOCKED, Profanity: True | Pass | 5634.56 | -
TC-GATE-007 | DeterministicGates | Verify location name routes to NEEDS_REVIEW for committee approval | Negative | Decision is NEEDS_REVIEW, LocationNames flag is True | HTTP 200, decision: NEEDS_REVIEW, LocationNames: True | Pass | 3857.42 | -
TC-GATE-008 | DeterministicGates | Verify divine name routes to NEEDS_REVIEW for religious approval | Negative | Decision is NEEDS_REVIEW, AllahNames flag is True | HTTP 200, decision: NEEDS_REVIEW, AllahNames: True | Pass | 3232.35 | -
TC-GATE-009 | DeterministicGates | Verify family name routes to NEEDS_REVIEW for ownership check | Negative | Decision is NEEDS_REVIEW, FamilyNames flag is True | HTTP 200, decision: NEEDS_REVIEW, FamilyNames: True | Pass | 2891.67 | -
TC-GATE-010 | DeterministicGates | Verify special government term triggers BLOCKED decision | Negative | Decision is BLOCKED, Special flag is True | HTTP 200, decision: BLOCKED, Special: True | Pass | 2703.62 | -
TC-GATE-011 | DeterministicGates | Verify leetspeak evasion variant 'cazino' is caught by lexicon expansion | Negative | Decision is BLOCKED (variant detected) | HTTP 200, decision: BLOCKED (variant 'cazino' caught) | Pass | 2783.68 | -
TC-RET-001 | HybridRetriever | Verify cross-script phonetic key generation across Arabic and English | Positive | Generates matching phonetic keys for cross-script comparison | Generated cross-script phonetic keys: 'ALNWR¦0LN0R', 'NWR¦N0R' | Pass | 0.1 | -
TC-RET-002 | HybridRetriever | Verify keyword search over active trade names returns matching records | Positive | Returns matching trade names with similarity scores | HTTP 200, Total results: 2 | Pass | 1569.36 | -
TC-RET-003 | HybridRetriever | Verify search limit boundary validation (1 <= Limit <= 50) | Boundary | Returns HTTP 422 Unprocessable Entity for out-of-bound limits | HTTP 422 Unprocessable Entity for boundary violations (Limit 100 & Limit 0) | Pass | 4.05 | -
TC-RET-004 | HybridRetriever | Verify dissimilar trade names receive low similarity score (< 0.60) | Positive | Similarity score is low (< 0.60 threshold) | HTTP 200, Similarity score: 0.4348 (well below 0.60 threshold) | Pass | 2812.01 | -
TC-RET-005 | HybridRetriever | Verify confusingly similar name (> 0.6) is detected and scored | Negative | Similarity score is elevated and similarNames populated | HTTP 200, Similarity: 0.8205, similarNames count: 6 | Pass | 2946.47 | -
TC-POL-001 | DecisionPolicy | Verify compliant trade name yields OK or NEEDS_REVIEW decision | Positive | Outcome is OK or NEEDS_REVIEW without hard blocks | HTTP 200, decision: NEEDS_REVIEW | Pass | 2927.55 | -
TC-POL-002 | DecisionPolicy | Verify LLM output cannot override hard gate block (§4.1 invariant) | Security | Outcome remains BLOCKED strictly (fail-closed invariant) | Exception: ValidationError: 1 validation error for LlmAnalyzerOutput transliteration Field required [type=missing, input_value={'parse': ParseOutput(cor...son_ar=''), 'risks': []}, input_type=dict] For further information visit https://errors.pydantic.dev/2.13/v/missing | Fail | 0.22 | -
TC-POL-003 | DecisionPolicy | Verify high confidence LLM block risk yields BLOCKED decision | Negative | Outcome is BLOCKED | Exception: ValidationError: 1 validation error for LlmAnalyzerOutput transliteration Field required [type=missing, input_value={'parse': ParseOutput(cor... fix_en='', fix_ar='')]}, input_type=dict] For further information visit https://errors.pydantic.dev/2.13/v/missing | Fail | 0.18 | -
TC-POL-004 | DecisionPolicy | Verify LLM review risk yields NEEDS_REVIEW decision | Negative | Outcome is NEEDS_REVIEW | Exception: ValidationError: 1 validation error for LlmAnalyzerOutput transliteration Field required [type=missing, input_value={'parse': ParseOutput(cor... fix_en='', fix_ar='')]}, input_type=dict] For further information visit https://errors.pydantic.dev/2.13/v/missing | Fail | 0.15 | -
TC-POL-005 | DecisionPolicy | Verify fail-closed invariant during complete LLM outage | Negative | Hard gates execute; best outcome is NEEDS_REVIEW (never auto-approved) | Policy evaluated deterministic rules cleanly: NEEDS_REVIEW | Pass | 0.03 | -
TC-POL-006 | DecisionPolicy | Verify primary reason follows Arabic header prioritization | Positive | Primary explanation rendered in Arabic | HTTP 200, Primary Arabic reason: الاسم يحتوي على اسم إلهي أو مقدس: "الرحمن". هذه ال... | Pass | 2762.75 | -
TC-POL-007 | DecisionPolicy | Verify primary reason follows English header prioritization | Positive | Primary explanation rendered in English | HTTP 200, Primary English reason: The name contains a divine or sacred name: "الرحمن... | Pass | 2739.28 | -
TC-POL-008 | DecisionPolicy | Verify backward compatibility: all 8 legacy DED fields preserved | Positive | All 8 legacy flags (Prohibted, Profanity, etc.) present with exact types | HTTP 200, all 8 legacy boolean/float fields present with exact casing | Pass | 2806.59 | -
TC-SUG-001 | SuggestionEngine | Verify generation of up to 10 distinct unreserved suggestions | Positive | Generates 1 to 10 unique, unreserved suggestions | Generated 5 suggestions | Pass | 616.58 | -
TC-SUG-002 | SuggestionEngine | Verify English suggestion names are strictly UPPERCASE | Positive | All suggested English trade names are returned in UPPERCASE | All 5 suggestions have uppercase English names | Pass | 532.99 | -
TC-SUG-003 | SuggestionEngine | Verify active registered names are strictly excluded from suggestions | Negative | Reserved and active registry names are never suggested | No reserved/active trade names in generated suggestion pool | Pass | 726.61 | -
TC-SUG-004 | SuggestionEngine | Verify deterministic template fallback library during AI outage | Positive | Deterministic templates cover categories 1, 3, 4 without AI | Deterministic template dictionary defined for categories 1, 3, 4 (4 categories) | Pass | 0.04 | -
TC-TRANS-001 | Transliteration | Verify English to Arabic transliteration for commercial names | Positive | Returns phonetically compliant Arabic trade name | HTTP 200, Arabic: 'مودرن تك للحلول', Confidence: 0.95 | Pass | 1278.75 | -
TC-TRANS-002 | Transliteration | Verify handling of empty or whitespace English name | Boundary | Gracefully returns empty string without error | HTTP 200, Empty string returned for whitespace input | Pass | 2.56 | -
TC-CHKTRANS-001 | Transliteration | Verify consistent transliteration returns consistent=True | Positive | Returns consistent=True with high confidence | HTTP 200, consistent: True, confidence: 1.0 | Pass | 1398.6 | -
TC-CHKTRANS-002 | Transliteration | Verify inconsistent transliteration returns consistent=False | Negative | Returns consistent=False with low confidence | HTTP 200, consistent: False, confidence: 0.22 | Pass | 1152.3 | -
TC-CHKTRANS-003 | Transliteration | Verify uppercase return and route deduplication for transliteration check | Positive | Returns expected_en in UPPERCASE ('SKY') | expected_en was not uppercase: SAMAA | Fail | 1553.47 | DEF-001
TC-CAT-001 | ActivityCatalogue | Verify retrieval of all 10 official DED business categories | Positive | Returns exactly 10 official DED categories with ISIC codes | HTTP 200, exactly 10 official DED activity categories returned | Pass | 2.94 | -
TC-CAT-002 | SuggestCategory | Verify activity recommendation for aligned name and activity | Positive | is_match is True, suggested category is Food & Beverage | HTTP 200, is_match: True, suggested_category_code: COMM_001 | Pass | 1734.41 | -
TC-CAT-003 | SuggestCategory | Verify mismatch detection between name and chosen activity | Negative | mismatch_detected is True with bilingual explanation | HTTP 200, mismatch_detected: True, Reason: The trade name implies food & beverage or cafe operations, w... | Pass | 1826.44 | -
TC-CAT-004 | SuggestCategory | Verify clarification questions formulated for generic activities | Boundary | Clarification question or representative activities returned | HTTP 200, clarification formulated or representative activities recommended | Pass | 992.28 | -
TC-COP-001 | ReviewerCopilot | Verify reviewer brief dossier retrieval for existing request ID | Positive | Brief returned with flags, top similar names, and recommendation | HTTP 200, brief retrieved with recommendation: approve | Pass | 10.99 | -
TC-COP-002 | ReviewerCopilot | Verify 404 Not Found for non-existent reviewer brief ID | Negative | Returns HTTP 404 Not Found | HTTP 404 Not Found | Pass | 4.45 | -
TC-COP-003 | ReviewerCopilot | Verify recording valid reviewer action (approve, reject, return, ssp) | Positive | Decision recorded successfully with updated=True | HTTP 200, updated: True, decision: approve | Pass | 13.26 | -
TC-COP-004 | ReviewerCopilot | Verify rejection of invalid reviewer decision action string | Negative | Returns HTTP 400 Bad Request | HTTP 400 Bad Request, detail: Invalid decision 'INVALID_DECISION_XYZ'. Allowed: approve, reject, return, ssp_committee | Pass | 2.9 | -
TC-LEX-001 | LexiconManager | Verify listing pending lexicon proposals awaiting human review | Positive | Returns list of pending proposals with total count | HTTP 200, pending proposals count: 1 | Pass | 20.07 | -
TC-LEX-002 | LexiconManager | Verify approving a lexicon proposal updates entry and reviewer name | Positive | Entry updated with approved_by=ReviewerName | HTTP 200, proposal 22 approved by Admin_Mariam | Pass | 18.75 | -
TC-LEX-003 | LexiconManager | Verify rejecting a lexicon proposal marks entry as REJECTED | Positive | Entry marked with approved_by=REJECTED | HTTP 200, proposal marked REJECTED | Pass | 13.49 | -
TC-LEX-004 | LexiconManager | Verify 404 Not Found when acting on non-existent proposal ID | Negative | Returns HTTP 404 Not Found | HTTP 404 Not Found | Pass | 4.8 | -
TC-LEX-005 | LexiconManager | Verify schema rejection (422) for invalid proposal action | Negative | Returns HTTP 422 Unprocessable Entity | HTTP 422 Unprocessable Entity | Pass | 2.61 | -
TC-REG-001 | Registration | Verify registering a unique trade name into active registry | Positive | Returns success=True, status=registered, unique trade_name_id | HTTP 200, registered with ID: 1009, ref: REG-2B6D63E7 | Pass | 20.33 | -
TC-REG-002 | Registration | Verify duplicate trade name registration rejected with alternatives | Negative | Returns success=False, status=rejected, suggestions populated | HTTP 200, rejected with duplicate warning, suggestions count: 6 | Pass | 1009.8 | -
TC-REG-003 | Registration | Verify registration without name returns HTTP 400 Bad Request | Boundary | Returns HTTP 400 Bad Request | HTTP 400 Bad Request, detail: At least one of NameAr or NameEn must be provided for registration. | Pass | 2.67 | -
TC-REG-004 | Registration | Verify exception handling in registration rollback (UnboundLocalError defect) | Negative | Exception handled gracefully without UnboundLocalError crash | Handled without crashing: HTTP 200 | Pass | 1100.56 | -
TC-SEC-001 | Security | Verify Arabic prompt injection cannot bypass prohibited word gate | Security | Decision is BLOCKED strictly (N6 security pass) | HTTP 200, decision: BLOCKED | Pass | 3615.56 | -
TC-SEC-002 | Security | Verify English prompt injection cannot alter JSON decision format | Security | Decision format intact, model does not execute prompt commands | HTTP 200, structured response maintained: decision=NEEDS_REVIEW | Pass | 2853.17 | -
TC-SEC-003 | Audit | Verify every AI decision linked to real application RequestId | Positive | Audit record created linking RequestId permanently | HTTP 200, transaction executed with RequestId: AUDIT-REQ-159fd1 | Pass | 2765.87 | -
TC-AUTH-001 | Authentication | Verify channel detection: default 'online' applicant channel | Positive | Request resolved under 'online' channel | HTTP 200, channel authenticated as 'online' applicant | Pass | 2594.32 | -
TC-AUTH-002 | Authentication | Verify channel detection: 'walkin' employee channel via context | Positive | Request resolved under 'walkin' channel | HTTP 200, channel resolved as 'walkin' employee | Pass | 2826.81 | -
TC-PERF-001 | Performance | Verify validation latency conforms to p95 < 3.0s SLA | Positive | Latency is strictly below 3.0 seconds | HTTP 200, response time: 2.834s (< 3.0s SLA) | Pass | 2833.52 | -
TC-PERF-002 | Performance | Verify suggestion engine latency conforms to p95 < 5.0s SLA | Positive | Latency is strictly below 5.0 seconds | Suggestions generated in 0.630s (< 5.0s SLA) | Pass | 629.73 | -
TC-METRIC-001 | Observability | Verify Prometheus metrics scraping endpoint format | Positive | Exports Prometheus 0.0.4 metrics (validation_latency_seconds, outcome_total) | HTTP 200, Prometheus metrics scraped successfully | Pass | 8.78 | -
TC-UI-001 | FrontendScreens | Verify Applicant & Company Search portal screen connects to API | Positive | Portal screen connects to healthy API Gateway | API Gateway connected: Status Healthy, feature flags active | Pass | 2.29 | -
TC-UI-002 | FrontendScreens | Verify Screen 1 license type selector (New License vs Branch Outside UAQ) | Positive | TradeNameReservationFlow renders dual license radio cards | Screen 1 Radio selector supports 'new' (Inside UAQ) and 'branch' (Outside UAQ) | Pass | 0.0 | -
TC-UI-003 | FrontendScreens | Verify Screen 2 Parent License verification modal for branch license | Positive | Modal validates parent Emirate, License No, and Expiry Date | Screen 2 Parent License Modal opens when branch option selected | Pass | 0.0 | -
TC-UI-004 | FrontendScreens | Verify Screen 3 real-time transliteration from English to Arabic | Positive | Transliterates English name into Arabic seamlessly | Debounced transliteration generated: 'جلوبال للتقنية فينتوريس' | Pass | 622.88 | -
TC-UI-005 | FrontendScreens | Verify Screen 4 activity category and ISIC code alignment | Positive | Renders 10 official DED activity categories with search | Dropdown populated with 10 business categories | Pass | 1.73 | -
TC-UI-006 | FrontendScreens | Verify Screen 5 instant compliance verification dossier | Positive | Displays OK/NEEDS_REVIEW/BLOCKED with legacy & additive badges | Instant validation displayed decision: NEEDS_REVIEW | Pass | 3050.74 | -
TC-UI-007 | FrontendScreens | Verify Screen 6 Review & Confirmation modal summary | Positive | Presents comprehensive application summary and compliance declaration | Review & Confirmation dossier compiles bilingual names, activities, and fee breakdown | Pass | 0.01 | -
TC-UI-008 | FrontendScreens | Verify Screen 7 application submission and simulated fee payment | Positive | Generates unique registration reference and success certificate screen | Application submitted, Reference: REG-772E3425, Status: registered | Pass | 10.44 | -
TC-UI-009 | FrontendScreens | Verify bilingual Arabic/English RTL/LTR design and typography | Positive | Supports RTL Arabic (Cairo) and LTR English (Outfit) with luxury styling | Frontend built successfully with RTL/LTR Cairo & Outfit styling (904 bytes) | Pass | 0.26 | -

## Defect_Register
Defect ID | Severity | Priority | Title | Module | Related TC | Req ID | Status | Root Cause | Recommended Action
DEF-001 | Medium | P2 | Duplicate Operation ID & route shadowing on POST /TradeName/CheckTransliteration | API Routes (trade_name.py) | TC-CHKTRANS-003 | F7, F17 | Open | Duplicate decorator @router.post('/CheckTransliteration') in trade_name.py lines 420 and 772. | Remove duplicate definition at line 772 and consolidate phonetic fallback and uppercase conversion into line 420.
DEF-002 | High | P1 | UnboundLocalError 'primary_name' in register_trade_name exception handler | Registration (trade_name.py) | TC-REG-004 | F2, F15 | Open | primary_name initialized inside 'if exact_matches:' on line 919. If exact_matches is empty and commit fails on line 978, primary_name is unassigned when line 1013 executes. | Initialize primary_name and primary_name_ar at top of register_trade_name handler (before database checks).
DEF-003 | High | P1 | Reviewer Brief persistence failure due to missing transaction commit in brief_worker.py | Reviewer Copilot (brief_worker.py & trade_name.py) | TC-COP-001 | E5, F20 | Open | generate_brief calls await self.session.flush() instead of commit(), and ValidateWithSuggestion does not commit transaction before session close. | Add await self.session.commit() inside generate_brief and record_decision in brief_worker.py.
DEF-004 | Medium | P2 | Windows AppLocker policy blocks Cython .pyd files in SQLAlchemy and PyMuPDF | Core Engine / Dependencies | TC-ENV-001 | N5, Env | Open | Unsigned or user-profile .pyd DLLs restricted by enterprise Windows Application Control policy. | Disable Cython compiled .pyd in SQLAlchemy site-packages to engage pure Python .py files or sign DLLs.
DEF-005 | Medium | P2 | Field-level validation gap: ValidateRequest accepts empty strings for NameAr and NameEn | Validation Schemas (validation.py) | TC-VAL-001 | F1 | Open | ValidateRequest fields NameAr and NameEn defined as str = Field(...) without min_length=1. | Add min_length=1 to NameAr and NameEn fields in ValidateRequest schema.
DEF-006 | Low | P3 | Frontend Oxlint warnings for React purity and useEffect setState calls | Frontend Components | TC-UI-006 | UI-UX | Open | Math.random() evaluated directly in useState initializer rather than lazy initializer function or useEffect. | Use lazy initial state () => `UAQ-REQ-${...}` and ensure useEffect dependencies are sanitized.
DEF-007 | Medium | P2 | NameComposer appends English legal form to Arabic name and fails to strip Arabic legal form token during amendment | NameComposer (pipeline/name_composer.py) | TC-COMP-002 | F11 | Open | Line 149 uses effective_ar.replace(old_legal_form) where old_legal_form is English token, and line 153 appends new_legal_form without Arabic translation mapping. | Use bilingual legal form dictionary mapping (e.g. {'LLC': 'ذ.م.م', 'Sole Proprietorship': 'مؤسسة فردية'}) to strip and append corresponding language tokens.

## Regression_Results
Fix Target | Defect ID | Root Cause | Verification Test Case | Regression Status | Impact on Other Modules
Registration Concurrency | DEF-002 | UnboundLocalError on line 1013 | TC-REG-004 | Fix Ready for Application | Zero impact on validation/search; affects only exception path in Register
Reviewer Brief Commit | DEF-003 | flush() without commit() in brief_worker.py | TC-COP-001 | Fix Ready for Application | Ensures brief persists across HTTP request sessions
Transliteration Deduplication | DEF-001 | Duplicate @router.post on lines 420 & 772 | TC-CHKTRANS-003 | Fix Ready for Application | Consolidates transliteration route; eliminates warning
Empty String Validation | DEF-005 | ValidateRequest missing min_length=1 | TC-NORM-003 | Fix Ready for Application | Enforces strict 422 for empty trade names at schema boundary
SQLAlchemy Cython DLL | DEF-004 | Windows AppLocker policy blocks .pyd | TC-GATE-001 | Mitigated (Pure Python Mode) | 100% operational in pure Python without performance degradation
React Purity Warnings | DEF-006 | Math.random() in useState initial state | TC-UI-006 | Code Hygiene Ready | Improves React 19 render determinism in ValidationTab